## Slide 1: Project Cost Management
PMI Knowledge Areas

## Slide 2: Project Cost Management Processes
Process Group | Cost Management Process | Major Output
Planning | CP1: Planning Cost Mgmt | Cost Management Plan
 | CP2: Estimating Costs | Activity Cost Estimates
 | CP3: Determining the Budget | Cost Performance Baseline
Monitoring and Controlling | MC1: Controlling Costs | Work Perf. Measurements Budget Forecasts

## Slide 3: Types of Costs and Benefits
Tangible costs or benefits
Intangible costs or benefits
Direct costs
Indirect costs
Sunk cost
Basic Principles of Cost Management
  Learning curve theory
  Reserves
    Contingency reserves
    Management reserves

## Slide 4: CP1: Planning Cost Management
The project team uses expert judgment, analytical techniques, and meetings to develop the cost management plan
A cost management plan includes:
  Level of accuracy and units of measure
  Organizational procedure links
  Control thresholds
  Rules of performance measurement
  Reporting formats
  Process descriptions

## Slide 5: CP2: Estimating Costs
Project managers must take cost estimates seriously if they want to complete projects within budget constraints
It’s important to know the types of cost estimates, how to prepare cost estimates, and typical problems associated with IT cost estimates
Input
1) HR Plan 2) Project Schedule 3) Scope Baseline 4) Risk Register
Tools/Techniques
1) EstimatingTechniques 2) Cost of Quality 3) Reserve Analysis 4) PM Estimate Software 5) Expert Judgment
Output
1) Activity cost estimates 2) Estimate Bases 3) Update docs

## Slide 6: My Health Intranet Sites
What are the primary costs for the intranet site project?
What is the best way to create estimates for the project?

## Slide 7: Categories of Cost Estimates
The number and type of cost estimates vary by application area.

## Slide 8: Cost Estimation Techniques
Basic tools and techniques for cost estimates:
  Top-down estimates
    Analogous
    Parametric modeling

## Slide 9: Cost Estimation Techniques
Basic tools and techniques for cost estimates:
  Bottom-up estimates
    PERT
      Ex. The pessimistic cost estimate for an activity is $11,000, the optimistic estimate is $3,000 and the most likely estimate is $4,000. What should you use for the expected estimate?

## Slide 10: Using Estimation Techniques
Top-Down Technique
  Externally: used by organizations completing IT projects for other companies
  Internally: can be used for similar projects
  Problem
    You are dealing with IT
    Less Accurate Estimates

## Slide 11: Using Estimation Techniques
Bottom-up Technique
  Based on the WBS
  Creates a detailed estimate of each work component
  More Accurate
    Can separate across phases
    Would be better for controlling costs (Monday’s lecture)

## Slide 12: Which technique is being used?
Based on the description below, what kind of estimate is being used?
It will take 20 hours of a programmer’s time to write this program. The average rate to hire a programmer is $50 per hour. Therefore, the cost of writing this program, assuming that everything else needed to write the program, such as a computer, is in place, is 20 x $50 = $1,000.

## Slide 13: Typical Problems with IT Cost Estimates
Estimates are done too quickly
People lack estimating experience
Human beings are biased toward underestimation
Management desires accuracy
Contingency reserve is often used to reduce the risk from these problems

## Slide 14: PM Network: Estimates are just that
“We are headed down the path of providing more precise estimates in an environment that is not as precise and where costs fluctuate greatly.”
Managing estimates through the lifecycle
Agile Estimating
Formulas for success

## Slide 15: PM Network: Estimating Errors
“treat estimates as a living process and not a one time event.”
Approaches
Matching Skill Sets
Share Accountability

## Slide 16: Review: Cost Estimate Technique (Parametric, Reserve Analysis, Bottom-up Estimate, Three-point estimate)
It was discovered that there are many unknowns about an activity and that it could cost a lot of more than estimated because it could take longer. So, some money is put aside to deal with the situation
There is a complicated activity for which there are many disagreements among the team about its cost estimate. So, an estimate was created by taking the average optimistic estimate, pessimistic estimate and realistic estimate.
The manager still had doubts about the estimate above so the complex activity was split up into smaller pieces. Estimate costs were placed on these pieces and then all were added up to reach the final figure/
For another activity, the number of work hours needed were multiplied by the hourly rate of a programmer

## Slide 17: CP3: Determining the Budget
Cost budgeting involves allocating the project cost estimate to individual work items over time
The WBS is a required input to the cost budgeting process since it defines the work items
Reserve analysis must occur
  Contingency reserves
  Management reserves

## Slide 18: Figure 7-4. Surveyor Pro Project Cost Baseline

## Slide 19: Chapter Summary
Project cost management is a traditionally weak area of IT projects, and project managers must work to improve their ability to deliver projects within approved budgets
Main processes include
  Plan cost management
  Estimate costs
  Determine the budget
  Control costs

## Slide 20: CAPM – Things to know
Project budget is time-phased project cost (aggregating individual activity costs)
Contingency Reserves
  Deal with uncertainties in schedule/cost
  Deal with overruns of the project objectives
Analogous estimating takes less time but is also less accurate
Memorize the formulas for EV, CV, CPI, PV, SV, SPI